URBANI — INTENSIVE PROTOTYPING DAYS (DPI)

Implementation & Execution Plan — September 28–29, 2026

1. Executive Purpose

This document serves as the operational execution plan for the Urbani AWS Intensive Prototyping Days (DPI), taking place on September 28–29, 2026 (09:00 AM – 05:00 PM daily). It defines the exact scope, task backlog, hour-by-hour schedule, builder assignments, AI Model configuration (Anthropic Claude 3.5 Sonnet v2 / anthropic.claude-3-5-sonnet-20241022-v2:0), evaluation criteria, and demonstration protocol for constructing a functional Proactive Observability MVP.

2. Objectives & Definition of Done

The primary goal of the 2-day DPI event is to deliver a fully functional, end-to-end working MVP that satisfies the following four Definition of Done (DoD) criteria:

Criterion 1 — Ingestion: Successfully ingest raw logs and metrics from at least one AWS Elastic Beanstalk application environment into Amazon CloudWatch.

Criterion 2 — AI Diagnosis: Detect a simulated application anomaly (e.g., connection pool exhaustion or memory leak) and generate a structured Bedrock troubleshooting recommendation using Claude 3.5 Sonnet v2 (anthropic.claude-3-5-sonnet-20241022-v2:0).

Criterion 3 — Persistence: Persist the generated alert and evidence recommendation into Amazon DynamoDB UrbaniAlerts table.

Criterion 4 — Visualization: Render active alerts, evidence log snippets, and performance metrics on a single unified dashboard (Amazon Managed Grafana / CloudWatch Dashboard).

3. Scope Declaration

[DPI BOUNDARIES] IN-SCOPE: Read-only telemetry ingestion, scheduled Lambda pre-processing, Bedrock model inference using Anthropic Claude 3.5 Sonnet v2 with Guardrails (urbani-dpi-guardrail-v1), DynamoDB alert persistence, and dashboard visualization. OUT-OF-SCOPE: Automated production remediation, webhook notifications (Slack/Teams/Email), VPC PrivateLink deployment, and multi-tenant billing integration.

4. Workstreams

WS1 — AWS Foundation & IAM: Account setup, IAM role provisioning, KMS keys, AWS Budgets alerts.

WS2 — Telemetry Ingestion: CloudWatch Log Groups & Elastic Beanstalk metric pipeline configuration.

WS3 — AI Analysis Engine: Lambda Collector, Bedrock Model access (anthropic.claude-3-5-sonnet-20241022-v2:0), System Prompt tuning (temperature: 0.0), Bedrock Guardrails.

WS4 — Persistence & Data: DynamoDB UrbaniAlerts schema creation, Lambda Alert Writer implementation.

WS5 — Dashboard Visualization: Centralized Grafana / CloudWatch dashboard setup for alerts, logs, and metrics.

WS6 — Validation & Testing: Controlled anomaly simulation, end-to-end pipeline execution, performance & cost auditing.

WS7 — Documentation & Handover: Architecture finalization, operational guide, post-DPI decision roadmap.

5. Detailed Task Backlog

The following task matrix assigns specific execution responsibilities across the Urbani and OneData prototyping team:

| ID | Task Description | Est. | AWS Services | Priority | Deps | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| T01 | Configure AWS sandbox account, base IAM roles, and AWS Budgets cost alerts | 1.0h | IAM, AWS Budgets | High | — | Urbani Dev 1 |
| T02 | Validate CloudWatch Logs & Metrics ingestion on target Elastic Beanstalk env | 1.5h | CloudWatch, Beanstalk | High | T01 | Urbani Dev 1 |
| T03 | Build Lambda Collector / Preprocessor (query CW logs/metrics, filter max 100 lines) | 3.0h | AWS Lambda, CloudWatch | High | T02 | Urbani Dev 2 |
| T04 | Configure EventBridge Scheduler rule for 5-minute periodic trigger | 1.0h | EventBridge | High | T03 | Urbani Dev 2 |
| T05 | Enable Amazon Bedrock Model access (anthropic.claude-3-5-sonnet-20241022-v2:0) & prompt tuning | 2.0h | Amazon Bedrock | High | T03 | Urbani Dev 1 |
| T06 | Configure Bedrock Guardrails (urbani-dpi-guardrail-v1) for PII filtering & Responsible AI | 1.5h | Bedrock Guardrails | Med | T05 | Urbani Dev 1 |
| T07 | Build Lambda Alert Writer to validate JSON schema and save alerts | 2.5h | AWS Lambda, DynamoDB | High | T05 | Urbani Dev 2 |
| T08 | Provision DynamoDB UrbaniAlerts table & GSI for pattern history | 2.0h | Amazon DynamoDB | Med | T05 | Urbani Dev 2 |
| T09 | Construct central Dashboard (Managed Grafana / CloudWatch Dashboard) | 3.0h | Grafana / CloudWatch | High | T02 | Urbani Dev 1 |
| T10 | End-to-End Testing: Simulate failure scenario & validate Claude 3.5 Sonnet diagnosis flow | 2.0h | Full Stack | High | T04,07,09 | Urbani Dev 1 & 2 |
| T11 | Audit IAM security roles, KMS encryption, and token cost consumption | 1.0h | IAM, CloudTrail, Budgets | High | T10 | OneData Architect |
| T12 | Dry-run demonstration scenario and refine prompt responses | 1.5h | Bedrock, Dashboard | High | T10 | Urbani & OneData |
| T13 | Prepare final presentation deck and executive demo walkthrough | 1.5h | PowerPoint / Output | Med | T12 | OneData Architect |
| T14 | Document final architecture decisions, operational runbook & post-DPI roadmap | 1.5h | Documentation | Med | T10 | Urbani Dev 2 |

6. Day 1 Detailed Operational Schedule (Sept 28, 2026)

09:00 – 09:30 AM

Activity: Kickoff, Scope Alignment & Pre-DPI Checklist Verification

Expected Output: Confirmed architecture & decision owners

09:30 – 10:30 AM

Activity: T01 & T02: AWS Sandbox Setup, IAM Roles & CloudWatch Telemetry Validation

Expected Output: CloudWatch log stream confirmed

10:30 – 12:30 PM

Activity: T03 & T05: Lambda Collector & Bedrock Claude 3.5 Sonnet v2 Access Enablement

Expected Output: Lambda querying CW & initial Bedrock test

12:30 – 01:30 PM

Activity: T04: EventBridge Scheduler 5-Min Cron Orchestration Setup

Expected Output: Scheduled invocation firing successfully

01:30 – 02:30 PM

Activity: LUNCH BREAK

Expected Output: —

02:30 – 04:00 PM

Activity: T07 & T08: DynamoDB UrbaniAlerts Schema & Lambda Alert Writer Build

Expected Output: Successful PutItem from Lambda to DB

04:00 – 05:00 PM

Activity: Day 1 Sync, Code Commit & Initial Pipeline Smoke Test

Expected Output: First automated alert persisted in DB

7. Day 2 Detailed Operational Schedule (Sept 29, 2026)

09:00 – 09:30 AM

Activity: Day 2 Standup & Task Prioritization Review

Expected Output: Tasks T09–T14 assigned

09:30 – 11:30 AM

Activity: T09: Centralized Dashboard Construction & Widget Wiring

Expected Output: Grafana/CW Dashboard rendering metrics

11:30 – 01:00 PM

Activity: T06 & T10: Bedrock Guardrails Setup & Controlled Anomaly Simulation

Expected Output: Simulated anomaly detected by Claude 3.5 Sonnet

01:00 – 02:00 PM

Activity: LUNCH BREAK

Expected Output: —

02:00 – 03:30 PM

Activity: T11 & T12: End-to-End Validation, Security/Cost Audit & Demo Dry-Run

Expected Output: Repeatable demo flow confirmed

03:30 – 04:30 PM

Activity: Executive Presentation & Live Technical Demonstration

Expected Output: Live MVP demo delivered to stakeholders

04:30 – 05:00 PM

Activity: T14: Post-DPI Retrospective & Roadmap Sign-off

Expected Output: Deliverables accepted & next steps defined

8. Controlled Demonstration Scenario

1. Inject Controlled Anomaly: Trigger a synthetic database connection exhaustion in the test Elastic Beanstalk app.

2. Telemetry Ingestion: App writes ERROR connection pool logs to CloudWatch Log Group /aws/elasticbeanstalk/urbani-app.

3. Scheduled Collector Execution: EventBridge fires Lambda Collector UrbaniTelemetryCollectorFn on its 5-minute cycle.

4. Telemetry Window Retrieval: Lambda fetches 100 recent log lines containing connection pool error codes.

5. Bedrock Inference: Lambda passes payload to Bedrock Claude 3.5 Sonnet v2 (anthropic.claude-3-5-sonnet-20241022-v2:0, temp: 0.0) with Guardrails active.

6. Structured Diagnosis: Bedrock identifies 'DatabaseConnectionTimeout' with 0.92 confidence score.

7. Persistence: Lambda Alert Writer UrbaniAlertWriterFn saves structured JSON alert record to DynamoDB UrbaniAlerts table.

8. Dashboard Visualization: Central Dashboard displays active red alert badge, evidence log snippet, and recommended runbook steps.

9. Developer Verification: Engineer Javier reviews dashboard, accepts recommendation, and executes fix.

9. Evaluation Criteria

Detection Accuracy: Does Claude 3.5 Sonnet v2 correctly identify the root cause of the simulated anomaly?

Evidence Relevance: Are the cited log lines directly relevant to the diagnosed issue?

Recommendation Quality: Are the suggested troubleshooting actions accurate and actionable?

Execution Latency: Does the end-to-end ingestion-to-alert loop complete in <30 seconds?

Token Cost Control: Does the invocation remain within the pre-filtered token budget (<$0.02 per run)?

10. Risks and Mitigation

11. Pre-DPI Readiness Checklist

12. Expected Deliverables

13. Post-DPI Plan & Next Steps